## Product Backlog Template
Status |  | Task | Assigned To | Sprint # | Active Sprint | Estimation | Actual Time | Feature
|  | Backlog |  | Active Sprint: |  | 1
Status | Complete Status | Task Name | Assigned To |  |  | H | H
Assigned | N/A | Login/Logout | Ge Bian | 1 | 1 | 0.5 |  | Required info: username & password
Assigned | N/A | Registration with/without Google account | Ge Bian | 1 | 1 | 3 |  | If signup without a google acount, requires the following info: 1. username;
2.password;
3.password confirm;
Assigned | N/A | Login and registration HTML file | Ge Bian | 1 | 1 | 1 |  | All HTML file will be implemented in Django template with Bootstrap
Assigned | N/A | Game Scene HTML file | Ge Bian | 1 | 1 | 4 |  | Main game scene contains a navbar wihich link to all other features, includes scoreboard, playback, logout,etc
Assigned | N/A | Scoreboard HTML file | Ge Bian | 1 | 1 | 1
Assigned | N/A | Using AJAX to GET the Scoreboard section through a link in the navbar in the main gain scene | Ge Bian | 1 | 1 | 2
Assigned | N/A | Game playback HTML file | Ge Bian | 1 | 1 | 1
Assigned | N/A | Character design and model implementation | Ge Bian | 1 | 1 | 4
Assigned | N/A | Game scene design and model construction | Ge Bian | 1 | 1 | 4
Assigned | N/A | Implement keyboard input stream | Sean Kuang | 1 | 1 | 6 |  | Keyboard stream will be recorded and stored in database with current status automatically every 3 seconds
Assigned | N/A | Implement the keyboard character control | Sean Kuang | 1 | 1 | 4 |  | Only implement the game as an in-memory component running at the web server
Assigned | N/A | Build the single user game with keyboard control mode | Sean Kuang | 1 | 1 | 6 |  | User are able to control character using keyboard, and will trigger victory controller after reaching the end
Unassigned
Unassigned
Unassigned
Current product manager: Ge Bian
Next prodcut manager: Sean Kuang