## Product Backlog Template
Status |  | Task | Assigned To | Sprint # | Estimation | Actual Time | Feature
|  | Backlog |  | Active Sprint: | 1
Status | Complete Status | Task Name | Assigned To |  | H | H
Assigned | N/A | Registration with Google account | Ge Bian | 2 | 2 |  | Considering register with Facebook account also
Assigned | N/A | Implement voice input stream | Ge Bian | 2 | 6
Assigned | N/A | Control character's movement by voice input | Ge Bian | 2 | 6 |  | Decide using tone or volume to control character's jumping?
Assigned | N/A | Modified game scene with a start button floating on top of the scene | Ge Bian | 2 | 6
Assigned | N/A | Add mode selection below the start button in the game scene | Ge Bian | 2 | 6
Assigned | N/A | implement update the ranking for keyboard mode | Ge Bian | 2 | 3
Assigned | N/A | implement update the ranking for voice mode | Ge Bian | 2 | 3
Assigned | N/A | CSRF token modified | Ge Bian | 2 | 3
Assigned | N/A | Modified getting the input using form | Ge Bian | 2 | 4
Assigned | N/A | Modified the game accessable only to logged-in users | Sean Kuang | 2 | 4
Assigned | N/A | Backend game status implementation (update every 5 seconds) for both mode | Sean Kuang | 2 | 10
Assigned | N/A | Rejoin after disconnected | Sean Kuang | 2 | 5
Assigned | N/A | implement game replay model | Sean Kuang | 2 | 5
Assigned | N/A | front end implementation of status update for both mode | Sean Kuang | 2 | 5
Unassigned
Current product manager: Sean Kuang
Next prodcut manager: Ge Bian