## Product Backlog Template
Status |  | Task | Assigned To | Sprint # | Estimation | Actual Time | Feature
|  | Backlog |  | Active Sprint: | 3
Status | Complete Status | Task Name | Assigned To |  | H | H
Assigned | N/A | UIUX improvement | Ge Bian | 3 | 10
Assigned | N/A | User testing | Ge Bian | 3 | N/A
Assigned | N/A | Value checking and validation | Ge Bian | 3 | 6
Assigned | N/A | Loadding page with instructions for new users before showing the real game page | Ge Bian | 3 | 8
Assigned | N/A | Considering rewrite switching between login/signup/logged-in | Ge Bian | 3 | 6
Assigned | N/A | Character sound effect | Ge Bian | 3 | 4 |  | Hit the ground & Jump & Run & Fall
Assigned | N/A | Background music | Ge Bian | 3 | 2
Assigned | N/A | UI re-design: Add drawer on the left side, move user information, ranking board, best game into it | Ge Bian | 3 | 4
Assigned | N/A | UI re-design: Move the content of ranking board and game list into two pop up window | Ge Bian | 3 | 4 |  | Bind these two window to the its related tag in the drawer
Assigned | N/A | Tolerance between background music and voice control mode | Ge Bian | 3 | 4
Assigned | N/A | Game playback list implementation and oncall function | Ge Bian | 3 | 2
Assigned | N/A | Character customization for each user | Ge Bian | 3 | 5
Assigned | N/A | Websoket build to enable real time reaction between players | Sean Kuang | 3 | 15
Assigned | N/A | Cloud deployment | Sean Kuang | 3 | 10
Assigned | N/A | Game playback animation implementation | Sean Kuang | 3 | 5
Assigned | N/A | game UI integration | Sean Kuang | 3 | 5
Assigned | N/A | Game complete animation and restart game without refreshing the page manually | Sean Kuang | 3 | 3
Current product manager: Ge Bian
Next prodcut manager: Sean Kuang